## PLANNED EXPENSES
Project P.E.T.E.R.S.
Detailed Expense Estimates
Shaded cells are calculations.
Planned Expenses | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Employee Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Wages | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
Benefits | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 81000
Subtotal | 31750 | 31750 | 31750 | 31750 | 31750 | 31750 | 31750 | 31750 | 31750 | 31750 | 31750 | 31750 | 381000
Office Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Office lease | 1720 | 1720 | 1720 | 1720 | 1720 | 1720 | 1720 | 1720 | 1720 | 1720 | 1720 | 1720 | 20640
Gas | 200 | 200 | 200 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 200 | 200 | 1350
Electric | 80 | 80 | 80 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 80 | 80 | 1450
Water | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 300
Telephone | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 300
Internet access | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900
Office supplies | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 480
Subtotal | 2165 | 2165 | 2165 | 2085 | 2085 | 2085 | 2085 | 2085 | 2085 | 2085 | 2165 | 2165 | 25420
*assuming 360 (90 a quarter) units are to be constructed in the first year of production using current equipment and commercial-off-the-shelf products
Unit Component Cost | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
(2) Micro-Bluetooth 4.0 LE | Jan: 17.98 | 17.98
(2) Micro-SD 16GB (Sony 70Mbps) | Jan: 17.98 | 17.98
(2) CanaKit Raspberry Pi-2 + Case | Jan: 93.98 | 93.98
(2) Reacon Snow2 (HUD) | Jan: 798 | 798
Reacon Snow2 (HUD + Goggles) | Jan: 549 | 549
(2) MLH05KPSL06A Pressure Sensor | Jan: 292.28 | 292.28
(2) Edimax EW-781Un Wi-Fi Adapter | Jan: 19.98 | 19.98
(2) AA Battery Pack | Jan: 38.98 | 38.98
Laser Diodes 5-pack | Jan: 11.89 | 11.89
Photo-Resistors 20-pack | Jan: 4.69 | 4.69
(2) Arduino Pro Mini | Feb: 10.5 | 10.5
LSM9DS0 Accelerometer/Gyroscope | Feb: 26.99 | 26.99
Misc Materials | Jan: 83.11 | 83.11
Subtotal | 1927.87 | 37.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1965.36
TOTALS
Monthly Planned Expenses | 35842.87 | 33952.49 | 33915 | 33835 | 33835 | 33835 | 33835 | 33835 | 33835 | 33835 | 33915 | 33915 | 408385.36
TOTAL Planned Expenses | 35842.87 | 69795.36 | 103710.36 | 137545.36 | 171380.36 | 205215.36 | 239050.36 | 272885.36 | 306720.36 | 340555.36 | 374470.36 | 408385.36

## ACTUAL EXPENSES
Project P.E.T.E.R.S.
Detailed Expense Estimates
Shaded cells are calculations.
Actual Expenses | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Employee Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Wages | Jan Jan: 85000; Feb Feb: 85000; Mar Mar: 85000; Apr Apr: 88000; May May: 88000; Jun Jun: 88000 | 519000
Benefits | 22950 | 22950 | 22950 | 23760 | 23760 | 23760 | 0 | 0 | 0 | 0 | 0 | 0 | 140130
Subtotal | 107950 | 107950 | 107950 | 111760 | 111760 | 111760 | 0 | 0 | 0 | 0 | 0 | 0 | 659130
Office Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Office lease | Jan: 9800; Feb: 9800; Mar: 9800; Apr: 9800; May: 9800; Jun: 9800 | 58800
Gas | Jan: 4; Feb: 430; Mar: 385; Apr: 230; May: 87; Jun: 88 | 1224
Electric | Jan: 288; Feb: 278; Mar: 268; Apr: 299; May: 306; Jun: 290 | 1729
Water | Jan: 35; Feb: 33; Mar: 34; Apr: 36; May: 34; Jun: 36 | 208
Telephone | Jan: 224; Feb: 235; Mar: 265; Apr: 245; May: 245; Jun: 220 | 1434
Internet access | Jan: 180; Feb: 180; Mar: 180; Apr: 180; May: 180; Jun: 180 | 1080
Office supplies | Jan: 256; Feb: 142; Mar: 160; Apr: 221; May: 256; Jun: 240 | 1275
Security | Jan: 600; Feb: 600; Mar: 600; Apr: 600; May: 600; Jun: 600 | 3600
Subtotal | 11387 | 11698 | 11692 | 11611 | 11508 | 11454 | 0 | 0 | 0 | 0 | 0 | 0 | 69350
Marketing Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Web site hosting | Jan: 500; Feb: 500; Mar: 500; Apr: 500; May: 500; Jun: 500 | 3000
Web site updates | Jan: 200; Feb: 200; Mar: 200; Apr: 200; May: 200; Jun: 1500 | 2500
Collateral preparation | Jan: 4800; Feb: 0; Mar: 0; Apr: 5500; May: 0; Jun: 0 | 10300
Collateral printing | Jan: 100; Feb: 500; Mar: 100; Apr: 100; May: 600; Jun: 180 | 1580
Marketing events | Jan: 1800; Feb: 2200; Mar: 2200; Apr: 4700; May: 1500; Jun: 2300 | 14700
Miscellaneous expenses | Jan: 145; Feb: 156; Mar: 123; Apr: 223; May: 187; Jun: 245 | 1079
Subtotal | 7545 | 3556 | 3123 | 11223 | 2987 | 4725 | 0 | 0 | 0 | 0 | 0 | 0 | 33159
Training/Travel | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Training classes | Jan: 1600; Feb: 2400; Mar: 1400; Apr: 1600; May: 1200; Jun: 2800 | 11000
Training-related travel costs | Jan: 1200; Feb: 2200; Mar: 1400; Apr: 1200; May: 800; Jun: 3500 | 10300
Subtotal | 2800 | 4600 | 2800 | 2800 | 2000 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 21300
TOTAL Planned Expenses
Monthly Actual Expenses | 129682 | 127804 | 125565 | 137394 | 128255 | 134239 | 0 | 0 | 0 | 0 | 0 | 0 | 782939
TOTAL Actual Expenses | 129682 | 257486 | 383051 | 520445 | 648700 | 782939 | 782939 | 782939 | 782939 | 782939 | 782939 | 782939

## EXPENSE VARIANCES
Project P.E.T.E.R.S.
Detailed Expense Estimates
All cells are calculations.
Expense Variances | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Employee Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Wages | -60000 | -60000 | -60000 | -63000 | -63000 | -63000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | -219000
Benefits | -16200 | -16200 | -16200 | -17010 | -17010 | -17010 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | -59130
Subtotal | -76200 | -76200 | -76200 | -80010 | -80010 | -80010 | 31750 | 31750 | 31750 | 31750 | 31750 | 31750 | -278130
Office Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Office lease | -8080 | -8080 | -8080 | -8080 | -8080 | -8080 | 1720 | 1720 | 1720 | 1720 | 1720 | 1720 | -38160
Gas | 196 | -230 | -185 | -180 | -37 | -38 | 50 | 50 | 50 | 50 | 200 | 200 | 126
Electric | -208 | -198 | -188 | -149 | -156 | -140 | 150 | 150 | 150 | 150 | 80 | 80 | -279
Water | -10 | -8 | -9 | -11 | -9 | -11 | 25 | 25 | 25 | 25 | 25 | 25 | 92
Telephone | -199 | -210 | -240 | -220 | -220 | -195 | 25 | 25 | 25 | 25 | 25 | 25 | -1134
Internet access | -105 | -105 | -105 | -105 | -105 | -105 | 75 | 75 | 75 | 75 | 75 | 75 | -180
Office supplies | -216 | -102 | -120 | -181 | -216 | -200 | 40 | 40 | 40 | 40 | 40 | 40 | -795
Security | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Subtotal | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Marketing Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Web site hosting | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Web site updates | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Collateral preparation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Collateral printing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Marketing events | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Miscellaneous expenses | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Training/Travel | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | YEAR
Training classes | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Training-related travel costs | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Subtotal | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
TOTALS
Monthly Expense Variances | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
TOTAL Expense Variances | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## EXPENSE ANALYSIS
Project P.E.T.E.R.S.
Detailed Expense Estimates
Expense Category | Planned Expenses | Actual Expenses | Expense Variances | Variance Percentage
Employee Costs | 381000 | 659130 | -278130 | -73%
Office Costs | 25420 | 69350 | -43930 | -172.8%
#REF! | #REF! | 33159 | #REF! | #REF!
Unit Component Cost | 1965.36 | 21300 | -19334.64 | -983.8%
TOTALS | 408385.36 | 782939 | -374553.64 | -91.72%