## Sheet1
Task | Start | Duration | End
Identify and Define Project Scope | 2015-09-21 | 7 | 2015-09-28
Determine Feasibility | 2015-09-26 | 2 | 2015-09-28
Research Available Technologies | 2015-09-26 | 7 | 2015-10-03
Develop Overall System Design | 2015-09-26 | 7 | 2015-10-03
Plan Logistics | 2015-09-30 | 3 | 2015-10-03
Develop Resource and Man-Power Allocation Plan | 2015-09-30 | 2 | 2015-10-02
Develop Network Architecture | 2015-10-02 | 6 | 2015-10-08
Develop Software Architecture | 2015-10-02 | 6 | 2015-10-08
Obtain Project Approval | 2015-10-05 | 10 | 2015-10-15
Obtain Hardware | 2015-10-05 | 36 | 2015-11-10
Develop GUI Framework and Required Utilities | 2015-10-07 | 28 | 2015-11-04
Develop Message Passing Standard | 2015-10-07 | 21 | 2015-10-28
Test and Evaluate Pressure Sensor Data Acquisition | 2015-10-14 | 14 | 2015-10-28
Familiarize With HUD SDK/API | 2015-10-28 | 4 | 2015-11-01
Test and Evaluate Laser Diode Feasibility | 2015-10-29 | 1 | 2015-10-30
Develop Android Packaging Process for Python Application | 2015-11-01 | 16 | 2015-11-17
Familiarize With HUD Interface | 2015-11-10 | 6 | 2015-11-16
Write Progress Report and Quad Chart | 2015-11-16 | 4 | 2015-11-20
Sideload Test Application to HUD | 2015-11-17 | 7 | 2015-11-24
Develop Presentation | 2015-11-23 | 10 | 2015-12-03
Hardware Packaging Design and Implementation | 2015-12-01 | 45 | 2016-01-15
Develop Data Transfer to HUD From Pi | 2015-12-03 | 7 | 2015-12-10
Implement Moving Map Subpanel | 2015-12-10 | 14 | 2015-12-24
Implement Low Pressure Indicator Subpanel | 2015-12-24 | 7 | 2015-12-31
Implement Paintball Level Indicator Subpanel | 2015-12-31 | 7 | 2016-01-07
Merge Subpanels to Single Application | 2016-01-07 | 14 | 2016-01-21
Implement Cross-User Communication | 2016-01-21 | 14 | 2016-02-04
Testing and Debugging | 2016-02-04 | 21 | 2016-02-25
Refining of Results | 2016-02-25 | 35 | 2016-03-31
Formulas:
End = [Start] + [Duration]

## Sheet2
Task | Start | Duration | End |  |  | Task | Start | Duration | End | Complete | Days Complete | Days Remaining
Identify and Define Project Scope | 2015-09-21 | 7 | 2015-09-28 | x |  | Identify and Define Project Scope | 2015-09-21 | 12 | 2015-10-03 | 100% | 12 | 0
Determine Feasibility | 2015-09-26 | 2 | 2015-09-28 |  |  | Team Allocation | 2015-09-30 | 3 | 2015-10-03 | 100% | 3 | 0
Research Available Technologies | 2015-09-26 | 7 | 2015-10-03 |  | Identify and Define Project Scope | Develop Software Architecture | 2015-10-02 | 6 | 2015-10-08 | 100% | 6 | 0
Develop Overall System Design | 2015-09-26 | 7 | 2015-10-03 |  |  | Obtain Project Approval | 2015-10-05 | 10 | 2015-10-15 | 100% | 10 | 0
Plan Logistics | 2015-09-30 | 3 | 2015-10-03 | x |  | Obtain and Evaluate Sensor Hardware | 2015-10-05 | 36 | 2015-11-10 | 100% | 36 | 0
Develop Resource and Man-Power Allocation Plan | 2015-09-30 | 2 | 2015-10-02 |  |  | Develop HUD, GUI, & Message Framework | 2015-10-07 | 28 | 2015-11-04 | 100% | 28 | 0
Develop Network Architecture | 2015-10-02 | 6 | 2015-10-08 | x |  | Test and Evaluate Laser Diode Feasibility | 2015-10-29 | 1 | 2015-10-30 | 100% | 1 | 0
Develop Software Architecture | 2015-10-02 | 6 | 2015-10-08 |  |  | Develop HUD Test Application | 2015-11-01 | 23 | 2015-11-24 | 100% | 23 | 0
Obtain Project Approval | 2015-10-05 | 10 | 2015-10-15 |  |  | Fall Progress Reports | 2015-11-16 | 17 | 2015-12-03 | 100% | 17 | 0
| 2015-10-05 | 36 | 2015-11-10 | x | Obtain and Evaluate Sensor Hardware | Hardware Packaging & Implementation | 2015-12-01 | 45 | 2016-01-15 | 4.444% | 2 | 43
Obtain and Evaluate Sensor Hardware | 2015-10-06 | 1 | 2015-10-07 |  |  | Implement HUD Subpanels | 2015-12-10 | 28 | 2016-01-07 | 0% | 0 | 28
Develop GUI Framework and Required Utilities | 2015-10-07 | 28 | 2015-11-04 | x |  | Merge Subpanels to Single Application | 2016-01-07 | 14 | 2016-01-21 | 0% | 0 | 14
Develop Message Passing Standard | 2015-10-07 | 21 | 2015-10-28 |  | Develop HUD, GUI, and Message Framework | Develop Cross Element Communication | 2015-12-03 | 65 | 2016-02-06 | 1.538% | 1 | 64
Familiarize With HUD SDK/API | 2015-10-28 | 4 | 2015-11-01 |  |  | Testing and Debugging | 2016-02-04 | 56 | 2016-03-31 | 0% | 0 | 56
Test and Evaluate Laser Diode Feasibility | 2015-10-29 | 1 | 2015-10-30 |  |  | Develop Subpanels
Develop Android Packaging Process for Python Application | 2015-11-01 | 16 | 2015-11-17 | x |  | Accelerometer Testing
Familiarize With HUD Interface | 2015-11-10 | 6 | 2015-11-16 |  | Develop HUD Test Application | Develop User Database & Communication Server
Sideload Test Application to HUD | 2015-11-17 | 7 | 2015-11-24 |  |  | Develop Sensor Data Acquisition Software
Write Progress Report and Quad Chart | 2015-11-16 | 4 | 2015-11-20 | x | Fall Progress Reports | Hopper Attachment Design & Iterations
Develop Presentation | 2015-11-23 | 10 | 2015-12-03 |  |  | Prepare Winter Reports
Hardware Packaging Design and Implementation | 2015-12-01 | 45 | 2016-01-15 |  |  | HUD Integration
Implement Moving Map Subpanel | 2015-12-10 | 14 | 2015-12-24 | x
Implement Low Pressure Indicator Subpanel | 2015-12-24 | 7 | 2015-12-31 |  | Implement HUD Subpanels
Implement Paintball Level Indicator Subpanel | 2015-12-31 | 7 | 2016-01-07
Merge Subpanels to Single Application | 2016-01-07 | 14 | 2016-01-21
Develop Data Transfer to HUD From Pi | 2015-12-03 | 7 | 2015-12-10 | x | Develop Cross Element Communication
Implement Cross-User Communication | 2016-01-21 | 14 | 2016-02-04
Testing and Debugging | 2016-02-04 | 21 | 2016-02-25 | x | Testing and Debugging
Refining of Results | 2016-02-25 | 35 | 2016-03-31
Formulas:
End = [Start] + [Duration]

## Sheet3
Identify and Define Project Scope | Identify and Define Project Scope
Determine Feasibility | Determine Feasibility
Research Available Technologies | Research Available Technologies
Develop Overall System Design | Develop Overall System Design
Plan Logistics | Plan Logistics
Develop Resource and Man-Power Allocation Plan | Develop Resource and Man-Power Allocation Plan
Develop Network Architecture | Develop Network Architecture
Develop Software Architecture | Develop Software Architecture
Obtain Project Approval | Obtain Project Approval
Obtain Hardware | Obtain Hardware
Develop GUI Framework and Required Utilities | Develop GUI Framework and Required Utilities
Develop Message Passing Standard | Develop Message Passing Standard | Develop Map Subpanel | Subpanel | Develop Subpanels
Familiarize With HUD SDK/API | Test and Evaluate Pressure Sensor Data Acquisition | Develop Low Pressure Indicator Subpanel |  | Accelerometer Testing
Develop Android Packaging Process for Python Application | Familiarize With HUD SDK/API | Develop Paintball Level Indicator Subpanel |  | Develop User Database and Communication Server
Familiarize With HUD Interface | Test and Evaluate Laser Diode Feasibility | Acquire & Test Accelerometer | Accel. Tests | Develop Sensor Data Acquisition Software
Write Fall Progress Report and Quad Chart | Develop Android Packaging Process for Python Application | Test Kalman Filter for Accelerometer |  | Hopper Attachment Design & Iterations
Sideload Test Application to HUD | Familiarize With HUD Interface | Develop User Database and Communication Server |  | Prepare Winter Reports
Develop Fall Presentation | Write Progress Report and Quad Chart | Develop Sensor Data Acquisition Software |  | HUD Integration
Develop Low Pressure Indicator Subpanel | Sideload Test Application to HUD | Hopper Attachment Design & Iterations
Develop Paintball Level Indicator Subpanel | Develop Presentation | Write Winter Progress Report and Quad Chart | Winter Reports
Acquire & Test Accelerometer | Hardware Packaging Design and Implementation | Develop Winter Presentation
Develop User Database and Communication Server | Develop Data Transfer to HUD From Pi | Transfer Data to HUD | HUD Integration
Develop Sensor Data Acquisition Software | Implement Moving Map Subpanel | Execute App on HUD
Develop Map Subpanel | Implement Low Pressure Indicator Subpanel
Hopper Attachment Design & Iterations | Implement Paintball Level Indicator Subpanel
Test Kalman Filter for Accelerometer | Merge Subpanels to Single Application
Merge Subpanels to Single Application | Implement Cross-User Communication
Write Winter Progress Report and Quad Chart | Testing and Debugging
Develop Winter Presentation | Refining of Results
Implement Cross-User Communication
Transfer Data to HUD
Execute App on HUD
Testing and Debugging
Refining of Results