## Sheet1
Task | Start | Duration | End
Identify and Define Project Scope | 2015-09-21 | 7 | 2015-09-28
Determine Feasibility | 2015-09-26 | 2 | 2015-09-28
Research Available Technologies | 2015-09-26 | 7 | 2015-10-03
Develop Overall System Design | 2015-09-26 | 7 | 2015-10-03
Plan Logistics | 2015-09-30 | 3 | 2015-10-03
Develop Resource and Man-Power Allocation Plan | 2015-09-30 | 2 | 2015-10-02
Develop Network Architecture | 2015-10-02 | 6 | 2015-10-08
Develop Software Architecture | 2015-10-02 | 6 | 2015-10-08
Obtain Project Approval | 2015-10-05 | 10 | 2015-10-15
Obtain Hardware | 2015-10-05 | 36 | 2015-11-10
Develop GUI Framework and Required Utilities | 2015-10-07 | 28 | 2015-11-04
Develop Message Passing Standard | 2015-10-07 | 21 | 2015-10-28
Familiarize With HUD SDK/API | 2015-10-28 | 4 | 2015-11-01
Develop Android Packaging Process for Python Application | 2015-11-01 | 16 | 2015-11-17
Familiarize With HUD Interface | 2015-11-10 | 6 | 2015-11-16
Write Fall Progress Report and Quad Chart | 2015-11-16 | 4 | 2015-11-20
Sideload Test Application to HUD | 2015-11-17 | 7 | 2015-11-24
Develop Fall Presentation | 2015-11-23 | 10 | 2015-12-03
Develop Low Pressure Indicator Subpanel | 2015-12-10 | 7 | 2015-12-17
Develop Paintball Level Indicator Subpanel | 2016-01-04 | 7 | 2016-01-11
Acquire & Test Accelerometer | 2016-01-04 | 6 | 2016-01-10
Develop User Database and Communication Server | 2016-01-07 | 45 | 2016-02-21
Develop Sensor Data Acquisition Software | 2016-01-07 | 45 | 2016-02-21
Develop Map Subpanel | 2016-01-11 | 14 | 2016-01-25
Hopper Attachment Design & Iterations | 2016-01-14 | 42 | 2016-02-25
Test Kalman Filter for Accelerometer | 2016-01-18 | 7 | 2016-01-25
Merge Subpanels to Single Application | 2016-01-25 | 14 | 2016-02-08
Write Winter Progress Report and Quad Chart | 2016-02-22 | 7 | 2016-02-29
Develop Winter Presentation | 2016-02-29 | 10 | 2016-03-10
Implement Cross-User Communication | 2016-03-13 | 14 | 2016-03-27
Transfer Data to HUD | 2016-03-13 | 7 | 2016-03-20
Execute App on HUD | 2016-03-21 | 7 | 2016-03-28
Testing and Debugging | 2016-04-01 | 30 | 2016-05-01
Refining of Results | 2016-04-01 | 30 | 2016-05-01
0
0
Formulas:
End = [Start] + [Duration]

## Sheet2
Task | Start | Duration | End |  |  | Task | Start | Duration | End | Complete | Days Complete | Days Remaining
Identify and Define Project Scope | 2015-09-21 | 7 | 2015-09-28 | x |  | Identify and Define Project Scope | 2015-09-21 | 12 | 2015-10-03 | 100% | 12 | 0
Determine Feasibility | 2015-09-26 | 2 | 2015-09-28 |  |  | Develop Software Architecture / Team Allocation | 2015-09-30 | 15 | 2015-10-15 | 100% | 15 | 0
Research Available Technologies | 2015-09-26 | 7 | 2015-10-03 |  | Identify and Define Project Scope | Obtain and Evaluate Sensor Hardware | 2015-10-05 | 36 | 2015-11-10 | 100% | 36 | 0
Develop Overall System Design | 2015-09-26 | 7 | 2015-10-03 |  |  | Develop HUD, GUI, & Message Framework | 2015-10-07 | 28 | 2015-11-04 | 100% | 28 | 0
Plan Logistics | 2015-09-30 | 3 | 2015-10-03 | x |  | Develop HUD Test Application | 2015-11-01 | 23 | 2015-11-24 | 100% | 23 | 0
Develop Resource and Man-Power Allocation Plan | 2015-09-30 | 2 | 2015-10-02 |  |  | Hardware Packaging & Implementation | 2015-12-01 | 45 | 2016-01-15 | 100% | 45 | 0
Develop Network Architecture | 2015-10-02 | 6 | 2015-10-08 | x |  | Implement HUD Subpanels | 2015-12-10 | 28 | 2016-01-07 | 100% | 28 | 0
Develop Software Architecture | 2015-10-02 | 6 | 2015-10-08 |  |  | Accelerometer Testing | 2016-01-04 | 21 | 2016-01-25 | 100% | 21 | 0
Obtain Project Approval | 2015-10-05 | 10 | 2015-10-15 |  |  | Develop User Database & Comm. Server | 2016-01-07 | 45 | 2016-02-21 | 100% | 45 | 0
| 2015-10-05 | 36 | 2015-11-10 | x | Obtain and Evaluate Sensor Hardware | Develop Sensor Data Acquisition Software | 2016-01-07 | 45 | 2016-02-21 | 100% | 45 | 0
Obtain and Evaluate Sensor Hardware | 2015-10-06 | 1 | 2015-10-07 |  |  | Hopper Attachment Design & Iterations | 2016-01-14 | 42 | 2016-02-25 | 100% | 42 | 0
Develop GUI Framework and Required Utilities | 2015-10-07 | 28 | 2015-11-04 | x |  | Revise / Finish Packaging | 2016-03-01 | 45 | 2016-04-15 | 100% | 45 | 0
Develop Message Passing Standard | 2015-10-07 | 21 | 2015-10-28 |  | Develop HUD, GUI, and Message Framework | Develop Wireless Air Tank Sensor Mount | 2016-03-01 | 20 | 2016-03-21 | 100% | 20 | 0
Familiarize With HUD SDK/API | 2015-10-28 | 4 | 2015-11-01 |  |  | HUD Integration / Comms with Server | 2016-03-13 | 15 | 2016-03-28 | 100% | 15 | 0
Test and Evaluate Laser Diode Feasibility | 2015-10-29 | 1 | 2015-10-30 |  |  | Cross User Communication | 2016-03-13 | 15 | 2016-03-28 | 100% | 15 | 0
Develop Android Packaging Process for Python Application | 2015-11-01 | 16 | 2015-11-17 | x |  | Testing and Debugging | 2016-04-01 | 30 | 2016-05-01 | 100% | 30 | 0
Familiarize With HUD Interface | 2015-11-10 | 6 | 2015-11-16 |  | Develop HUD Test Application
Sideload Test Application to HUD | 2015-11-17 | 7 | 2015-11-24
Write Progress Report and Quad Chart | 2015-11-16 | 4 | 2015-11-20 | x | Fall Progress Reports
Develop Presentation | 2015-11-23 | 10 | 2015-12-03
Hardware Packaging Design and Implementation | 2015-12-01 | 45 | 2016-01-15
Implement Moving Map Subpanel | 2015-12-10 | 14 | 2015-12-24 | x
Implement Low Pressure Indicator Subpanel | 2015-12-24 | 7 | 2015-12-31 |  | Implement HUD Subpanels
Implement Paintball Level Indicator Subpanel | 2015-12-31 | 7 | 2016-01-07
Merge Subpanels to Single Application | 2016-01-07 | 14 | 2016-01-21
Develop Data Transfer to HUD From Pi | 2015-12-03 | 7 | 2015-12-10 | x | Develop Cross Element Communication
Implement Cross-User Communication | 2016-01-21 | 14 | 2016-02-04
Testing and Debugging | 2016-02-04 | 21 | 2016-02-25 | x | Testing and Debugging
Refining of Results | 2016-02-25 | 35 | 2016-03-31
Formulas:
End = [Start] + [Duration]